## ADNOC Material Tracker
Architectural Material Tracker by Building
Architectural materials only. Quantities are best-effort approximations where derivable; verify against final IFC takeoff.
| Project Name | ADNOC GAS LONG TERM - EXECUTE STAGE PROJECT 5.0 (P5)
| Owner | ADNOC GAS OPERATIONS & MARKETING LLC
| EPCM | AMEC INTERNATIONAL LTD (WOOD)
| Contractor | Sinopec Nanjing
| Sub-contractor for Civil and Building Supplying | NHC International Trading LLC
SN | Building | System | Material Category | Material Name | ADNOC Spec Ref | International Standard | Description | Approved vendor by ADNOC | Brand | Origin | Unit | Quantity | Submittal Status | Consultant Approval | Client Approval | AVL Status | PO Status | Production Status | Delivery Status | Site Status | Installation Status
1 | IES-201 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1214.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
2 | IES-201 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1214.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
3 | IES-201 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1214.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
4 | IES-201 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 1214.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
5 | IES-201 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
6 | IES-201 | Partitions | Partitions | Gypsum board partition system | AGES-SP-01-017 / GG-000-20-40-002 |  | 16mm gypsum board / dry wall partition system | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
7 | IES-201 | Internal Finishes | Plaster / Mortar | Plastering, screed & accessories | AGES-SP-01-017 |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
8 | IES-201 | Flooring | Floor System | Raised access floor system | GG-000-20-40-003 |  | Modular raised floor system for equipment rooms |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
9 | IES-201 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
10 | IES-201 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
11 | IES-201 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
12 | IES-201 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
13 | IES-201 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
14 | IES-201 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
15 | IES-201 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
16 | IES-201 | Roof Drainage | Metal Works | Metal roof sheets / flashing / downspout | AGES-SP-01-002 / roof details |  | Corrugated/single-skin metal roofing, flashings, downspouts, overflow pieces | FLOWLINE MECHANICAL ENGINEERING FZC / Local manufacture ¦ ONYX INDUSTRIES (FZC) / Local manufacture ¦ Al Jazira Metal Industries - LLC - / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
17 | IES-201 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
18 | IES-201 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
19 | IES-201 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
20 | IES-201 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
21 | IES-201 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
22 | IES-201 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
23 | IES-202 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1016.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
24 | IES-202 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1016.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
25 | IES-202 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1016.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
26 | IES-202 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 1016.4 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
27 | IES-202 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
28 | IES-202 | Partitions | Partitions | Gypsum board partition system | AGES-SP-01-017 / GG-000-20-40-002 |  | 16mm gypsum board / dry wall partition system | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
29 | IES-202 | Internal Finishes | Plaster / Mortar | Plastering, screed & accessories | AGES-SP-01-017 |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
30 | IES-202 | Flooring | Floor System | Raised access floor system | GG-000-20-40-003 |  | Modular raised floor system for equipment rooms |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
31 | IES-202 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
32 | IES-202 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
33 | IES-202 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
34 | IES-202 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
35 | IES-202 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
36 | IES-202 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
37 | IES-202 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
38 | IES-202 | Roof Drainage | Metal Works | Metal roof sheets / flashing / downspout | AGES-SP-01-002 / roof details |  | Corrugated/single-skin metal roofing, flashings, downspouts, overflow pieces | FLOWLINE MECHANICAL ENGINEERING FZC / Local manufacture ¦ ONYX INDUSTRIES (FZC) / Local manufacture ¦ Al Jazira Metal Industries - LLC - / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
39 | IES-202 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
40 | IES-202 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
41 | IES-202 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
42 | IES-202 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
43 | IES-202 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
44 | IES-202 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
45 | IES-203 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1336.8 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
46 | IES-203 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1336.8 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
47 | IES-203 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 1336.8 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
48 | IES-203 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 1336.8 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
49 | IES-203 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
50 | IES-203 | Partitions | Partitions | Gypsum board partition system | AGES-SP-01-017 / GG-000-20-40-002 |  | 16mm gypsum board / dry wall partition system | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
51 | IES-203 | Internal Finishes | Plaster / Mortar | Plastering, screed & accessories | AGES-SP-01-017 |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
52 | IES-203 | Flooring | Floor System | Raised access floor system | GG-000-20-40-003 |  | Modular raised floor system for equipment rooms |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
53 | IES-203 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
54 | IES-203 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
55 | IES-203 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
56 | IES-203 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
57 | IES-203 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
58 | IES-203 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
59 | IES-203 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
60 | IES-203 | Roof Drainage | Metal Works | Metal roof sheets / flashing / downspout | AGES-SP-01-002 / roof details |  | Corrugated/single-skin metal roofing, flashings, downspouts, overflow pieces | FLOWLINE MECHANICAL ENGINEERING FZC / Local manufacture ¦ ONYX INDUSTRIES (FZC) / Local manufacture ¦ Al Jazira Metal Industries - LLC - / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
61 | IES-203 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
62 | IES-203 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
63 | IES-203 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
64 | IES-203 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
65 | IES-203 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
66 | IES-203 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
67 | SS-201 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 2480.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
68 | SS-201 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 2480.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
69 | SS-201 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 2480.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
70 | SS-201 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 2480.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
71 | SS-201 | Substructure Protection | Waterproofing | Self-adhesive membrane | Type 2a / firewall-protection details |  | 1.5mm self-adhesive membrane / foundation-firewall protection | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
72 | SS-201 | Substructure Protection | Plaster / Mortar | Plastering, screed & accessories | Screed beneath self-adhesive membrane |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
73 | SS-201 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
74 | SS-201 | Partitions | Partitions | Gypsum board partition system | AGES-SP-01-017 / GG-000-20-40-002 |  | 16mm gypsum board / dry wall partition system | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
75 | SS-201 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
76 | SS-201 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
77 | SS-201 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
78 | SS-201 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
79 | SS-201 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
80 | SS-201 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 / protection details |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
81 | SS-201 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
82 | SS-201 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
83 | SS-201 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
84 | SS-201 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
85 | SS-201 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
86 | SS-201 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
87 | SS-201 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
88 | SS-202 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
89 | SS-202 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
90 | SS-202 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
91 | SS-202 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
92 | SS-202 | Substructure Protection | Waterproofing | Self-adhesive membrane | Type 2a / firewall-protection details |  | 1.5mm self-adhesive membrane / foundation-firewall protection | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
93 | SS-202 | Substructure Protection | Plaster / Mortar | Plastering, screed & accessories | Screed beneath self-adhesive membrane |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
94 | SS-202 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
95 | SS-202 | Partitions | Partitions | Gypsum board partition system | AGES-SP-01-017 / GG-000-20-40-002 |  | 16mm gypsum board / dry wall partition system | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
96 | SS-202 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
97 | SS-202 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
98 | SS-202 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
99 | SS-202 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
100 | SS-202 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
101 | SS-202 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 / protection details |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
102 | SS-202 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
103 | SS-202 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
104 | SS-202 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
105 | SS-202 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
106 | SS-202 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
107 | SS-202 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
108 | SS-202 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
109 | SS-203 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
110 | SS-203 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
111 | SS-203 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
112 | SS-203 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 0 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
113 | SS-203 | Substructure Protection | Waterproofing | Self-adhesive membrane | Type 2a / firewall-protection details |  | 1.5mm self-adhesive membrane / foundation-firewall protection | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
114 | SS-203 | Substructure Protection | Plaster / Mortar | Plastering, screed & accessories | Screed beneath self-adhesive membrane |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
115 | SS-203 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
116 | SS-203 | Partitions | Partitions | Gypsum board partition system | AGES-SP-01-017 / GG-000-20-40-002 |  | 16mm gypsum board / dry wall partition system | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
117 | SS-203 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
118 | SS-203 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
119 | SS-203 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
120 | SS-203 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
121 | SS-203 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
122 | SS-203 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 / protection details |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
123 | SS-203 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
124 | SS-203 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
125 | SS-203 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
126 | SS-203 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
127 | SS-203 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
128 | SS-203 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
129 | SS-203 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
130 | OMS-201 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
131 | OMS-201 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
132 | OMS-201 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
133 | OMS-201 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
134 | OMS-201 | Roof | Metal Works | Metal roof sheets / flashing / downspout | 0.7mm PVDF coated galvanized sheet / flashing details |  | Corrugated/single-skin metal roofing, flashings, downspouts, overflow pieces | FLOWLINE MECHANICAL ENGINEERING FZC / Local manufacture ¦ ONYX INDUSTRIES (FZC) / Local manufacture ¦ Al Jazira Metal Industries - LLC - / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
135 | OMS-201 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
136 | OMS-201 | Internal Finishes | Plaster / Mortar | Plastering, screed & accessories | AGES-SP-01-017 |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
137 | OMS-201 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
138 | OMS-201 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
139 | OMS-201 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
140 | OMS-201 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
141 | OMS-201 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
142 | OMS-201 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 / external ramps/steps |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
143 | OMS-201 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
144 | OMS-201 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
145 | OMS-201 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
146 | OMS-201 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
147 | OMS-201 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
148 | OMS-201 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
149 | OMS-201 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
150 | OMS-203 | Roof | Waterproofing | SBS waterproofing membrane | AGES-SP-01-017 / GG-000-20-40-007 |  | 4mm torch-applied SBS membrane for roofs | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
151 | OMS-203 | Roof | Waterproofing | Bitumen primer | AGES-SP-01-017 / ASTM D41 | ASTM D41 | Cold bitumen primer conforming to ASTM D41 | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
152 | OMS-203 | Roof | Waterproofing | Geotextile separation layer | AGES-SP-01-017 / GG-000-20-40-007 |  | 140 g/sq.m geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
153 | OMS-203 | Roof | Insulation | XPS insulation board | AGES-SP-01-017 / GG-000-20-40-007 |  | 75mm extruded polystyrene roof insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | 162.6 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
154 | OMS-203 | Roof | Metal Works | Metal roof sheets / flashing / downspout | 0.7mm PVDF coated galvanized sheet / flashing details |  | Corrugated/single-skin metal roofing, flashings, downspouts, overflow pieces | FLOWLINE MECHANICAL ENGINEERING FZC / Local manufacture ¦ ONYX INDUSTRIES (FZC) / Local manufacture ¦ Al Jazira Metal Industries - LLC - / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
155 | OMS-203 | Walls | Wall System | Concrete blocks / masonry units | AGES-SP-01-017 |  | 200mm solid or hollow blocks for internal walls | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
156 | OMS-203 | Internal Finishes | Plaster / Mortar | Plastering, screed & accessories | AGES-SP-01-017 |  | 20mm plaster; cementitious accessories; screed support items | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
157 | OMS-203 | Flooring | Floor Finish | Anti-static PVC / rubber flooring | AGES-SP-01-014 |  | Anti-static PVC tiles and heavy-duty rubber flooring accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
158 | OMS-203 | Flooring | Floor Finish | Ceramic / vitrified / non-slip tiles | AGES-SP-01-014 |  | Floor & wall tiles incl. chemical resistant/vitrified accessories | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
159 | OMS-203 | Ceiling | Ceiling | Aluminium ceiling panels | AGES-SP-01-014 |  | 0.7mm powder-coated aluminium false ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
160 | OMS-203 | Ceiling | Insulation | Rockwool acoustic insulation | AGES-SP-01-014 |  | 50mm rockwool above false ceiling | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
161 | OMS-203 | External Finishes | Coating | General building paint | AGES-SP-01-014 |  | Acrylic / emulsion paint systems for internal architectural finishes | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
162 | OMS-203 | Protection | Coating | Epoxy / polyurethane protective coating | AGES-SP-01-014 / external ramps/steps |  | High-build weather-resistant epoxy; floor/ramp traffic deck systems | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
163 | OMS-203 | Joints | Sealant | Sealant / joint membrane system | AGES-SP-01-017 |  | Waterproof joint sealant, backing rod, membrane, joint accessories | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) | TBD | TBD | m | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
164 | OMS-203 | Doors | Doors | Fire rated doors | AGES-SP-01-016 |  | Fire rated steel doors (typically 1.5h to 3h per drawing schedules) | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
165 | OMS-203 | Doors | Doors | Metallic / blast resistant doors | AGES-SP-01-016 / FERA basis |  | Metal doors incl. blast resistant / external equipment doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) | TBD | TBD | No. | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
166 | OMS-203 | Doors | Hardware | Door hardware & access accessories | AGES-SP-01-016 |  | Locks, handles, closers, panic bars, thresholds, weatherstrips | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) | TBD | TBD | set | TBD | HOLD | HOLD | HOLD | Approved List Available | Not Released | Not Started | Not Delivered | Not Installed | Not Started
167 | OMS-203 | External Works | Paving | Interlocking paving / gravel / aggregate base | AGES-SP-01-005 / AGES-STD-01-019/022 |  | Light/heavy duty interlock paving and granular base materials | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
168 | OMS-203 | External Works | Metal Works | Handrails / ladders / rail accessories | Standard architectural details |  | Handrail, ladder and railing systems | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture | TBD | TBD | set | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
169 | OMS-203 | External Works | Treatment | Anti-termite treatment | AGES-SP-01-013 Cl. 9.32 |  | Preventive anti-termite treatment with 10-year warranty |  | TBD | TBD | m² | TBD | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started

## Quantity Basis
Building | Approx Roof Area (m²) | Basis / Note
IES-201 | 1214.4 | Approximate roof-plan takeoff from uploaded architectural drawings; verify against final IFC measurement.
IES-202 | 1016.4 | Approximate roof-plan takeoff from uploaded architectural drawings; verify against final IFC measurement.
IES-203 | 1336.8 | Approximate roof-plan takeoff from uploaded architectural drawings; verify against final IFC measurement.
SS-201 | 2480.6 | Approximate roof-plan takeoff from uploaded architectural drawings; verify against final IFC measurement.
SS-202 |  | Not reliably derivable from currently uploaded drawings; final takeoff required.
SS-203 |  | Not reliably derivable from currently uploaded drawings; final takeoff required.
OMS-201 | 162.6 | Approximate roof-plan takeoff from uploaded architectural drawings; verify against final IFC measurement.
OMS-203 | 162.6 | Approximate roof-plan takeoff from uploaded architectural drawings; verify against final IFC measurement.

## AVL Reference
Material Name | Example ADNOC-approved suppliers / manufacturers
SBS waterproofing membrane | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates)
Bitumen primer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates)
Geotextile separation layer | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates)
Self-adhesive membrane | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates)
XPS insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) ¦ TRIZAC ABUDHABI - SOLE PROPRIETORSH / ASPEN AEROGELS INC (United States of America)
Wall insulation board | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) ¦ TRIZAC ABUDHABI - SOLE PROPRIETORSH / ASPEN AEROGELS INC (United States of America)
Rockwool acoustic insulation | EMIRATES EXTRUDED POLYSTYRENE L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture ¦ TRAVERSE INTERNATIONAL INSULATION M / Armacell Middle East Co WLL (Bahrain) ¦ TRIZAC ABUDHABI - SOLE PROPRIETORSH / ASPEN AEROGELS INC (United States of America)
Concrete blocks / masonry units | FUJAIRAH CONCRETE PRODUCTS / Local manufacture ¦ EXEED LITECRETE - SOLE PROPRIETORSH / Local manufacture ¦ Al Emaar Cement Products Factory / Local manufacture ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture
Gypsum board partition system | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture
Plastering, screed & accessories | RIMAL ENGINEERING PRODUCTS LLC / CONMIX LTD. (United Arab Emirates) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ TERRACO UAE Ltd.Co LLC / Local manufacture ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture
Aluminium ceiling panels | Knauf RAK FZE / Local manufacture ¦ Gemini Technical Industries - Sole / Local manufacture ¦ METAFORM INDUSTRIES LLC / Local manufacture
Ceramic / vitrified / non-slip tiles | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) ¦ SULTACO GENERAL TRADING LLC / Gold Art Ceramica S.p.A / Energie k (Italy)
Anti-static PVC / rubber flooring | Al Khaleej Ceramics Co LLC / Local manufacture ¦ SULTACO GENERAL TRADING LLC / DEUTSCHE STEINZEUG INTERNATIONAL GM (Germany) ¦ SULTACO GENERAL TRADING LLC / Ceramica Rondine (Italy) ¦ SULTACO GENERAL TRADING LLC / Gold Art Ceramica S.p.A / Energie k (Italy)
Raised access floor system
Fire rated doors | White Aluminium Enterprises LLC / Local manufacture ¦ PETRO MIDDLE EAST - L.L.C - S.P.C / RAPP BOMEK AS (Norway) ¦ Al Rimal International Security & S / Al Kuhaimi Metal Industries Ltd. (Saudi Arabia) ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates)
Metallic / blast resistant doors | QMI Building Metal Products Manufac / Local manufacture ¦ DHABIA TRADING - SOLE PROPRIETORSHI / NATIONAL FIRE FIGHTING MANUFACTURIN (United Arab Emirates) ¦ TM Utley Truesea Doors and windows / Truesea Services (United Arab Emirates) ¦ SQUARE INDUSTRIES L.L.C / Local manufacture
Door hardware & access accessories | NEXTECH GENERAL TRADING - L.L.C - O / ENWARE PTY LTD (Australia) ¦ ALMIDIAFF INTERNATIONAL CO. L L C / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates) ¦ White Aluminium Enterprises LLC / Local manufacture
Aluminium & glazing systems | White Aluminium Enterprises LLC / Local manufacture ¦ BAIT AL NOKHADA TENTS & FABRIC SHAD / Local manufacture ¦ Alumil Tech Gulf LLC / Local manufacture
General building paint | STONCOR MIDDLE EAST L.L.C. / Local manufacture ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates) ¦ JOTUN ABU DHABI L.L.C / Local manufacture ¦ HENKEL POLYBIT INDUSTIES LIMITED / Local manufacture
Epoxy / polyurethane protective coating | LIWA PETROLEUM & INDUSTRIAL SUPPLIE / DURAPOL LIMITED (United Kingdom) ¦ ABU DHABI MARITIME & MERCANTILE INT / SHERWIN,WILLIAMS PROTECTIVE AND MAR (United Kingdom) ¦ PPG INDUSTRIES MIDDLE EAST L L C / PPG COATINGS EUROPE B.V. (Netherlands) ¦ BIN MOOSA & DALY LIMITED LLC / WINN & COALES (DENSO) LTD. (United Kingdom)
Sealant / joint membrane system | BERGER PAINTS EMIRATES LTD CO (LLC) / BERGER PAINTS EMIRATES LTD. (LLC) (United Arab Emirates) ¦ SULTACO GENERAL TRADING LLC / SERVICISED LTD (GCP Applied Technol (United Kingdom) ¦ SAP & KAPS PETROLEUM SERVICES - LLC / VIP Coatings International GmbH KG (Germany) ¦ SIKA INTERNATIONAL CHEMICALS L.L.C / SIKA UAE (United Arab Emirates)
Metal roof sheets / flashing / downspout | FLOWLINE MECHANICAL ENGINEERING FZC / Local manufacture ¦ ONYX INDUSTRIES (FZC) / Local manufacture ¦ Al Jazira Metal Industries - LLC - / Local manufacture ¦ JESER ALSADAH TRADING / WURTH GULF FZE (United Arab Emirates)
Metal fasteners & fixing accessories | VAN LEEUWEN PIPE AND TUBE MIDDLE EA / Industria Meccanica Ligure SPA (Italy) ¦ TECHNICAL PARTS ESTABLISHMENT / S.I STUD INC. (United States of America) ¦ FOHMICS OIL AND GAS EQUIPMENTS TRAD / ZheJiang Weigao Standard Parts Co. (China) ¦ TECHNO POLE INDUSTRIES LLC. / Local manufacture
Interlocking paving / gravel / aggregate base | Fujairah National Quarry / Local manufacture ¦ EMIRATES LINK TECHNOLOGY LLC / MBI GLOBAL LLC (United States of America) ¦ Emirates Marketing & Services L.L.C / Watad For General Supplies Co.LTD. (Jordan) ¦ EMIRATES STEEL INDUSTRIES CO PJS (E / Local manufacture
Sanitary ware & fittings | AL HADHOUDH TRADING & CONTRACTING E / SAUDI CERAMIC COMPANY (Saudi Arabia) ¦ SULTACO GENERAL TRADING LLC / Fluidmaster Group (Parent Company o (Slovenia) ¦ SULTACO GENERAL TRADING LLC / GEESA B.V. (Netherlands) ¦ SULTACO GENERAL TRADING LLC / KWC ME LLC (United Arab Emirates)
Handrails / ladders / rail accessories | RIMAL ENGINEERING PRODUCTS LLC / STRONGWELL CORPORATION (United States of America) ¦ INTERNATIONAL GRATING INCORPORATION / Local manufacture ¦ OASIS METAL MANUFACTURING LLC / Local manufacture ¦ ALMIDIAFF INTERNATIONAL CO. L L C / INTERNATIONAL GRATING INCORPORATION (United Arab Emirates)
Anti-termite treatment