## ADNOC Material Tracker
Architectural & Structural Material Tracker by Building | Architectural and structural materials extracted from CAD drawings and specification documents
Project Name | 123
Owner | 123
EPCM | 123
Contractor
Sub-Contractor
Project No. | 123
SN | Building | Unit | System | Material Category | Material Name | ADNOC Spec Ref | International Standard | Description | Approved Vendor by ADNOC | Brand | Origin | Unit | Quantity | Drawing Ref | Submittal Status | Consultant Approval | Client Approval | AVL Status | PO Status | Production Status | Delivery Status | Site Status | Installation Status
1 | OMS-201 | TBD | Foundation | Foundation | 200mm solid block wall |  |  | 200mm solid block wall | TBD | TBD | TBD | TBD | TBD | 30201_50150_LT_HE-H4-278-20-22-001, 30001_50501_LT_JE-ME-278-73-03-004, HE-278-20-22-001, HE-H4-278-20-22-001 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
2 | OMS-201 | TBD | Column | Column | Concrete |  |  | Concrete | TBD | TBD | TBD | TBD | TBD | 30201_50150_LT_HE-H4-278-20-22-001, 30001_50501_LT_JE-ME-278-73-03-004, HE-278-20-22-001, HE-H4-278-20-22-001 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
3 | OMS-201 | TBD | Foundation | Foundation | T16-150 |  |  | T16-150 | TBD | TBD | TBD | TBD | TBD | 30201_50150_LT_HE-H4-278-20-22-001, 30001_50501_LT_JE-ME-278-73-03-004, HE-278-20-22-001, HE-H4-278-20-22-001 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
4 | OMS-201 | TBD | Foundation | Foundation | T10-150 |  |  | T10-150 | TBD | TBD | TBD | TBD | TBD | 30201_50150_LT_HE-H4-278-20-22-001, 30001_50501_LT_JE-ME-278-73-03-004, HE-278-20-22-001, HE-H4-278-20-22-001 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
5 | OMS-201 | TBD | Foundation | Foundation | RC WALL |  |  | RC WALL | TBD | TBD | TBD | TBD | TBD | 30201_50150_LT_HE-H4-278-20-22-001, 30001_50501_LT_JE-ME-278-73-03-004, HE-278-20-22-001, HE-H4-278-20-22-001 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started
6 | OMS-201 | TBD | Column | Column | T20-BF |  |  | T20-BF | TBD | TBD | TBD | TBD | TBD | 30201_50150_LT_HE-H4-278-20-22-001, 30001_50501_LT_JE-ME-278-73-03-004, HE-278-20-22-001, HE-H4-278-20-22-001 | Pending | Pending | Pending | Available | RFQ | Not Started | Not Delivered | Not Installed | Not Started

## Quantity Basis
Building | Approx Roof Area (m²) | Basis / Note
OMS-201 | 165 | Roof area takeoff from architectural drawings: 30201_50150_LT_HE-H4-278-20-22-001, 30001_50501_LT_JE-ME-278-73-03-004, HE-278-20-22-001, HE-H4-278-20-22-001

## AVL Reference
Material Name | ADNOC-Approved Suppliers / Manufacturers | Notes / Performance Requirements
200mm solid block wall | TBD
Concrete | TBD
T16-150 | TBD
T10-150 | TBD
RC WALL | TBD
T20-BF | TBD